| Subject Code 19OE1CB10 |  |  | HT No. |  |  |  |  |  |  |  |  |  |  |  |  | R19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

VNR VIGNANA JYOTHI INSTITUTE OF ENGINEERING AND TECHNOLOGY

(AUTONOMOUS)

B.Tech. IV Year II Semester Regular Examinations, May 2023

IT PROJECT MANAGEMENT

(CSBS-Open Elective)

Time: 3 hours                                                                                 		      	 Max. Marks: 60

Answer ALL questions in PART-A.

Answer any ONE question from each unit in PART-B.

All Questions Carry Equal Marks.

PART-A

6X2=12M

|  | List the stages of Project Life Cycle. |  | CO-1 | BL-1 |
| --- | --- | --- | --- | --- |
|  | List the differences between PERT and CPM. |  | CO-2 | BL-1 |
|  | What is meant by risk and explain the different types of risks. |  | CO-2 | BL-2 |
|  | What is Agile? |  | CO-3 | BL-1 |
|  | List SCRUM development activities. |  | CO-4 | BL-1 |
|  | What is DevOps? |  | CO-4 | BL-1 |

PART-B

6X8=48M

| UNIT-1 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | List and Explain the Market and Demand Analysis and Discuss the key steps in the analysis. | 8M | CO-1 | BL-2 |
| OR |  |  |  |  |
|  | State and discuss Tools and Techniques to Estimate Project Costs | 8M | CO-1 | BL-2 |
| UNIT-2 |  |  |  |  |
|  | A small engineering project consists of 6 activities namely ABCDE & F with duration of 4, 6, 5, 4, 3 and 3 days respectively. Draw the network diagram and calculate EST, LST, EFT, LFT and floats. Mark the critical path and find total project duration. Activity; A; B; C; D; E; F. Preeceding; _; A; B; A; D; C,E. Duration; 4; 6; 5; 4; 3; 3. | 8M | CO-2 | BL-4 |
| OR |  |  |  |  |
|  | Illustrate with an example the difference between Resource leveling and Resource smoothing. | 8M | CO-2 | BL-3 |
| UNIT-3 |  |  |  |  |
|  | Define what project control is and explain its importance in project management. | 8M | CO-2 | BL-2 |
| OR |  |  |  |  |
|  | What are the different types of risks that can impact a project, and how do you identify them? | 8M | CO-2 | BL-3 |
| UNIT-4 |  |  |  |  |
|  | What is IT Service Management (ITIL), and how does it relate to Agile methodologies? | 8M | CO-3 | BL-2 |
| OR |  |  |  |  |
|  | How do you implement Agile software development practices in an organization, and what are the benefits and challenges? | 8M | CO-3 | BL-2 |
| UNIT-5 |  |  |  |  |
|  | Evaluate the effectiveness of Scrum methodology in a software development project and propose recommendations for improvement. | 8M | CO-4 | BL-3 |
| OR |  |  |  |  |
|  | What is a Sprint in Scrum methodology, and how does it differ from traditional software development approaches? | 8M | CO-4 | BL-2 |
| UNIT-6 |  |  |  |  |
|  | Analyze the differences and similarities between XP methodology and other Agile methodologies, such as Scrum. | 8M | CO-4 | BL-2 |
| OR |  |  |  |  |
|  | What is configuration management, and how does it improve DevOps processes? | 8M | CO-4 | BL-2 |

***